Vision & Scope Document

Building Materials Warehouse Management System (BMWMS) Report 1

| Project Name | Building Materials Warehouse Management System (BMWMS) |
| --- | --- |
| Version | v1.0.0 |
| Date Created | 15/05/2026 |
| Last Updated | 01/06/2026 |
| Author(s) |  |
| Reviewer(s) |  |
| Status | In Review |

# Document Change History

| Version | Date | Changes | Author |
| --- | --- | --- | --- |
| v1.0.0 | 01/06/2026 | Initial creation | [Author] |

# Table of Contents

Document Change History	1

Table of Contents	2

1. Project Overview	3

1.1 System Description	3

1.2 Technical Scope Summary	3

2. Development Team	3

2.1 Team Structure	3

2.2 RACI by Deliverable Type	3

2.3 Capacity Planning	4

3. Deliverable & Scope	4

3.1 Timeline Overview	5

3.2 Project Deliverables	5

3.3 Scope and Workload	6

a. Iteration 1 (Weeks 5–7)	6

b. Iteration 2 (Weeks 8–10)	7

c. Iteration 3 (Weeks 11–13)	7

4. Risks and Mitigations	8

5. Communication Plan	9

6. Configuration Management	9

6.1 Document Management	9

6.2 Source Code Management	10

6.3 Tools & Infrastructures	10

1. Product Background	12

2. Existing Solutions	12

2.1  Microsoft Excel	13

2.2  Sapo	13

2.3  KiotViet	13

3. Proposed Solution	15

4. Project Scope & Limitations	16

4.1  Major Features	16

4.2  Limitations & Exclusions	17

5. Expected Contributions & Next Steps	17

5.1  Business & Operational Impact	17

5.2  User Experience Impact	17

5.3  Planned Next Steps After Project Completion	18

# 1. Project Overview

## 1.1 System Description

Xuan Thanh Construction and Trading Co., Ltd. is a company specializing in the trading and distribution of construction materials. Currently, most warehouse management activities are performed manually using paper documents and spreadsheets.

Warehouse staff spend a significant amount of time recording inventory transactions, checking stock levels, and preparing reports. To properly record an inbound transaction with full item details, it theoretically takes 10 to 15 minutes. Because this manual process is so time-consuming during peak hours, warehouse staff have developed a harmful workaround: they skip itemized logging entirely and only record the total invoice value. This directly causes the company to lose complete visibility over physical stock right from the receiving stage. Similarly, processing an outbound transaction takes 8 to 12 minutes because staff must manually verify stock availability and prepare paper-based delivery notes.

The company does not currently have a standardized process for managing returned goods, inventory shrinkage, or stock discrepancies. Transaction records are stored in paper documents, making it difficult to track inventory movement history, investigate discrepancies, and retrieve information when needed.

Inventory counting is performed only at the end of each month. Each inventory audit typically requires 4 to 6 working hours and involves both warehouse personnel and accounting staff. Reconciling physical inventory with recorded inventory is time-consuming, and identifying the causes of discrepancies is often difficult due to incomplete transaction records.

In addition, warehouse items are not systematically organized or assigned to specific storage locations. Employees often spend 5 to 10 minutes locating a particular item, especially for high-volume or infrequently requested construction materials.

Inventory, stock movement, and accounts receivable/payable reports are generated manually at the end of each month. The accounting and warehouse management teams spend approximately one full working day collecting and consolidating data before reports can be produced. As a result, management lacks real-time visibility into inventory levels and business performance, limiting their ability to make timely purchasing and sales decisions.

As the number of products, suppliers, and customers continues to grow, the current manual warehouse management approach can no longer effectively support business operations. This results in increased risks of inventory loss, data inaccuracies, operational inefficiencies, and reduced business performance.

BMWMS (Building Materials Warehouse Management System) is a web-based warehouse management system designed for construction material trading companies. The system helps warehouse managers and warehouse staff manage inventory, inbound and outbound operations, stock taking, warehouse transfers, supplier information, and reporting activities in a centralized platform, replacing manual spreadsheet and paper-based processes.

## 1.2 Technical Scope Summary

| Metric | Value |
| --- | --- |
| Business Flows | 10 (BF01–BF10) |
| Actors / Roles | 5 |
| Use Cases | 89 (UC01–UC89) |
| Total FT-IDs | 27 Features |
| Screens / Pages | 60+ Screens |
| Background Jobs | 3 (Low Stock Alert, Inventory Recalculation, Scheduled Reports) |

# 2. Development Team

## 2.1 Team Structure

| Role | Code | Primary responsibilities |
| --- | --- | --- |
| Business Analyst / Project Manager | BA | Requirement elicitation, PRD, Use Case Specification, Feature Design Specification, project planning, sprint coordination, user manual, final documentation. |
| Developer 1 (Team Lead) | D1 | System architecture, database design, code review, deployment support, development of Module 1 (Warehouse Management) and Module 2 (Product Management). |
| Developer 2 | D2 | Development of Module 3 (Supplier Management), Module 4 (Inbound Management), and related integration tasks. |
| Developer 3 | D3 | Development of Module 5 (Outbound Management), Module 6 (Stock Taking), Module 7 (Warehouse Transfer), and Module 8 (Reporting & Analytics). |
| QA Engineer (Tester) | QA | Test planning, test case design, system testing, integration testing, defect tracking, UAT support, test reporting. |

## 2.2 RACI by Deliverable Type

R~Responsible (does the work)  ·  A~Accountable (approves quality)  ·  C~Consulted  ·  I~Informed

| Deliverable | TL | BA | D1 | D2 | QA |
| --- | --- | --- | --- | --- | --- |
| Deliverable | BA | D1 (TL) | D2 | D3 | QA |
| Vision & Scope | R/A | C | I | I | I |
| Project Management Plan | R/A | C | I | I | I |
| PRD | R/A | C | C | C | C |
| UCS | R/A | C | C | C | C |
| FDS | R/A | C | I | I | C |
| Database Design | C | R/A | C | C | I |
| Architecture Design | C | R/A | I | I | C |
| Test Plan | C | C | I | I | R/A |
| Feature Code – Module 1-2 | I | A/R | I | I | I |
| Feature Code – Module 3-4 | I | A | R | I | I |
| Feature Code – Module 5-8 | I | A | I | R | I |
| L1 Unit Tests | I | R | R | R | C |
| L2 Integration Tests | I | C | R | R | C |
| L3 System Tests | I | I | I | I | R/A |
| L4 UAT Support | C | I | I | I | R |
| Bug Fixing | I | R | R | R | C |
| Deployment Guide | C | R/A | I | I | I |
| User Manual | R/A | C | I | I | C |
| Final Report | R/A | C | I | I | C |

## 2.3 Capacity Planning

| Item | Value |
| --- | --- |
| Hours per person per week | 40 h |
| Team total per week | 200 h/week |
| Total duration | 14 weeks |
| Gross capacity | 2,800 h |
| Buffer (20%) | 560 h |
| Effective working capacity | 2,240 h |

# 3. Deliverable & Scope

## 3.1 Timeline Overview

| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase | Phase 1 | Phase 1 | Phase 1 | Phase 1 | Iter 1 | Iter 1 | Iter 1 | Iter 2 | Iter 2 | Iter 2 | Iter 3 | Iter 3 | Iter 3 | Closure |
| Deliverable | Planning | Analysis | Design | Design | Build | Build | Test | Build | Build | Test | Build | Build | UAT | Final |

| Role | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TL | Arch | Arch | DBD | Rev | CR | Rev | Int | Rev | Int | Rev | DG | E2E | E2E | DEP |
| BA | V&S | PRD | UCS1 | FDS1 | UCS2 | FDS2 | Rev | SS | Rev | SS | UM | UM | UAT | FR |
| D1 | Env | M01 | M02 | M02 | Code | Code | UT | M04 | M04 | IT | M06 | M07 | Fix | DEP |
| D2 | Env | M03 | M03 | M05 | Code | Code | UT | M05 | M05 | IT | M08 | M08 | Fix | DEP |
| QA | Setup | TC | TC | TP | TD | Rev | L3 | TD | Rev | L3 | Reg | E2E | UAT | AT |

## 3.2 Project Deliverables

| Deliverable | Completion phase / Deadline | Owner |
| --- | --- | --- |
| Vision & Scope | Phase 1 – Week 1 | BA |
| Project Management Plan v1.0 | Phase 1 – Week 1 | BA |
| PRD v1.0 | Phase 1 – Week 2 | BA |
| Architecture Design | Phase 1 – Week 3 | TL |
| Database Design | Phase 1 – Week 3 | TL |
| UCS v1.0 (M01–M04) | Phase 1 – Week 3 | BA |
| FDS v1.0 (M01–M04) | Phase 1 – Week 4 | BA |
| Test Plan v1.0 | Phase 1 – Week 4 | QA |
| UCS v1.0 (M05–M08) | Iteration 1 – Week 5 | BA |
| FDS v1.0 (M05–M08) | Iteration 1 – Week 6 | BA |
| Software Package – Iteration 1 (M01–M03) | Iteration 1 – Week 7 | TL + Dev |
| Unit & Integration Test Report – Iteration 1 | Iteration 1 – Week 7 | QA |
| Software Package – Iteration 2 (M04–M05) | Iteration 2 – Week 10 | TL + Dev |
| Unit & Integration Test Report – Iteration 2 | Iteration 2 – Week 10 | QA |
| Software Package – Iteration 3 (M06–M08) | Iteration 3 – Week 12 | TL + Dev |
| System Test & E2E Report | Iteration 3 – Week 13 | QA |
| UAT Sign-off Report | Iteration 3 – Week 13 | QA + BA |
| Deployment Guide | Phase 3 – Week 14 | TL |
| User Manual | Phase 3 – Week 14 | BA |
| Final Report | Phase 3 – Week 14 | BA |
| Project Handover Package | Phase 3 – Week 14 | TL + BA |

## 3.3 Scope and Workload

### a. Iteration 1 (Weeks 5–7)

Business Outcome: Foundation master data management for warehouse operations.

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-01 | Manage Warehouse | Must | Warehouse Management | UC01-UC05 | SC-01 |
| FT-02 | Manage Storage Location | Must | Warehouse Management | UC06-UC09 | SC-01 |
| FT-03 | Locate Product | Should | Warehouse Management | UC10 | SC-07 |
| FT-04 | Manage Product | Must | Product Management | UC11-UC15 | SC-02 |
| FT-05 | Manage Product Group | Must | Product Management | UC16-UC18 | SC-02 |
| FT-06 | Manage Product Attributes | Must | Product Management | UC19-UC20 | SC-02 |
| FT-07 | Product Transaction History | Should | Product Management | UC21 | SC-07 |
| FT-08 | Manage Supplier | Must | Supplier Management | UC22-UC26 | SC-03 |
| FT-09 | Supplier Product Management | Must | Supplier Management | UC27 | SC-03 |
| FT-10 | Supplier Transaction History | Should | Supplier Management | UC28 | SC-03 |

End-of-Iteration-1 Outcome

Users can manage warehouse structures, products, product attributes, and suppliers. The system provides complete master data required for warehouse operations.

### b. Iteration 2 (Weeks 8–10)

Business Outcome: Inventory receiving and issuing processes are operational.

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-11 | Manage Inbound Voucher | Must | Inbound Management | UC29-UC33 | SC-04 |
| FT-12 | Perform Receiving | Must | Inbound Management | UC34-UC35 | SC-04 |
| FT-13 | Inbound History | Should | Inbound Management | UC36 | SC-04 |
| FT-14 | Manage Outbound Voucher | Must | Outbound Management | UC37-UC41 | SC-05 |
| FT-15 | Stock Availability Check | Must | Outbound Management | UC42 | SC-05 |
| FT-16 | Perform Outbound | Must | Outbound Management | UC43 | SC-05 |
| FT-17 | Outbound History | Should | Outbound Management | UC44 | SC-05 |

End-of-Iteration-2 Outcome

Warehouse staff can receive goods, issue goods, and maintain accurate inventory records. Stock availability is validated before outbound transactions.

### c. Iteration 3 (Weeks 11–13)

Business Outcome: Inventory control, transfer, and reporting functions are completed.

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-18 | Stocktake Planning | Must | Audit | UC45-UC47 | SC-08 |
| FT-19 | Execute Stocktake | Must | Audit | UC48-UC49 | SC-08 |
| FT-20 | Inventory Adjustment | Must | Audit | UC50 | SC-09 |
| FT-21 | Stocktake History | Should | Audit | UC51 | SC-08 |
| FT-22 | Transfer Request Management | Must | Transfer | UC52-UC55 | SC-06 |
| FT-23 | Execute Transfer | Must | Transfer | UC56-UC57 | SC-06 |
| FT-24 | Inventory Reports | Must | Reporting | UC58-UC62 | SC-10 |
| FT-25 | Product Analytics | Should | Reporting | UC63-UC67 | SC-10 |
| FT-26 | Warehouse Analytics | Should | Reporting | UC68-UC72 | SC-10 |

End-of-Iteration-3 Outcome

Users can perform stocktaking, inventory adjustments, warehouse transfers, and generate management reports for warehouse operations.

# 4. Risks and Mitigations

| # | Risk | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | Requirements change during development | Medium | High | Freeze PRD and UCS after Week 4. Any change request must be reviewed by BA and approved by TL before implementation. |
| R02 | Delay in completing UI design and FDS documents | Medium | Medium | Prioritize core screens first. Complete UI and FDS one iteration ahead of development. |
| R03 | Integration issues between frontend and backend modules | Medium | High | Define API contracts before coding. Conduct integration testing at the end of each iteration. |
| R04 | Inventory transaction logic contains defects affecting stock accuracy | Medium | High | Implement unit tests for stock calculations and validate transaction flows with test scenarios before release. |
| R05 | Team members unavailable due to academic workload or exams | Medium | Medium | Maintain task buffer and cross-train team members to reduce dependency on a single developer. |
| R06 | Testing activities delayed due to late feature completion | Medium | High | Reserve buffer in Weeks 12–13 for regression testing and bug fixing before UAT. |
| R07 | UAT feedback requires significant rework | Low | High | Conduct internal review and demo after each iteration to identify issues before formal UAT. |
| R08 | Deployment environment differs from development environment | Low | Medium | Prepare deployment guide early and perform deployment rehearsal before final release. |
| R09 | Database design changes after development starts | Low | High | Finalize ERD and database schema during Phase 1 and review with the whole team before implementation. |
| R10 | Project schedule overrun near submission deadline | Medium | High | Track progress weekly, prioritize Must-have features, and postpone non-critical enhancements if required. |

# 5. Communication Plan

| Meeting | Frequency | Duration | Participants |
| --- | --- | --- | --- |
| Meeting | Frequency | Duration | Participants |
| Daily Stand-up | Every working day | 15 min | TL, BA, D1, D2, QA |
| Iteration Planning | Start of each iteration (Weeks 5, 8, 11) | 2 h | All |
| Weekly Progress Meeting | Every Friday | 30 min | All |
| Iteration Review (Demo) | End of each iteration (Weeks 7, 10, 13) | 1 h | All + Supervisor |
| Iteration Retrospective | After each review | 45 min | Team only |
| Requirements Review | Week 2 | 2 h | BA, TL, Dev Team |
| Design Review | Week 4 | 2 h | TL, BA, Dev Team |
| Test Plan Review | Week 4 | 1 h | QA, TL, BA |
| UAT Review | Week 13 | 1 h | BA, QA, Supervisor |
| Final Project Review | Week 14 | 1 h | All |

# 6. Configuration Management

## 6.1 Document Management

Project documents are stored and managed using Google Drive with role-based access control. All project members have access to shared project documents, while modification permissions are restricted based on responsibilities.

Document Versioning Rules

- Major versions: v1.0, v2.0, v3.0

- Minor revisions: v1.1, v1.2, v1.3

- All changes must be tracked using document version history.

- Only the document owner may approve major version updates.

- Final approved documents are marked as Baseline and stored in the Final Deliverables folder.

## 6.2 Source Code Management

Source code is managed using GitHub and follows a Git-based branching strategy.

Branch Structure

main

develop

feature/module-01

feature/module-02

feature/module-03

…

Source Control Rules

- main contains production-ready code only.

- develop contains integrated code for testing.

- Each feature is developed in a separate feature branch.

- Pull Requests are required before merging into develop.

- Code review must be approved by the Tech Lead.

- Commit messages follow the format:

[Module] Short description

Example:

[M01] Add warehouse creation API

[M04] Implement inbound voucher validation

Release Management

- Iteration 1 Release: Week 7

- Iteration 2 Release: Week 10

- Iteration 3 Release: Week 13

- Final Release: Week 14

## 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Razor Pages (.NET 8), ASP.NET Core Web API (.NET 8) |
| Database | Microsoft SQL Server 2022 |
| IDEs / Editors | Visual Studio 2022, Visual Studio Code |
| Diagramming | Draw.io, StarUML |
| Documentation | Microsoft Office 365, Google Docs, Google Sheets |
| Version Control | GitHub, Google Drive |
| Project Management | Jira, GitHub Projects |
| API Testing | Postman |
| UI/UX Design | Figma |
| Deployment Server | Windows Server / IIS |
| Source Repository | GitHub |
| Communication | Microsoft Teams, Discord |
| Testing Tools | xUnit, Swagger UI, Postman |
| Database Tools | SQL Server Management Studio (SSMS) |
| CI/CD (Optional) | GitHub Actions |

# 1. Product Background

Nowadays, Xuan Thanh Construction and Trading Co., Ltd., like many small and medium-sized distributors specializing in construction materials, still manages its entire warehouse operations using manual record-keeping methods, paper documents, and fragmented Excel spreadsheets. While this traditional approach may work when the volume of transactions is low, it becomes increasingly difficult to manage as the business expands its product catalogs, supplier networks, and customer bases. Maintaining control over inventory flows without a centralized digital tool creates a severe operational ceiling that limits the company's future scalability.

On a typical working day, Xuan Thanh's warehouse staff are responsible for receiving goods, arranging storage zones, processing outbound fulfillment requests, and checking physical stock levels. Currently, properly recording a single inbound transaction with full itemized details theoretically takes 10 to 15 minutes. Because this manual process is so time-consuming during peak hours and delays incoming transport trucks, warehouse staff have developed a harmful workaround: they skip itemized logging entirely and only record the total invoice monetary value. Similarly, processing a standard outbound transaction takes 8 to 12 minutes because staff must manually verify stock availability and prepare paper-based delivery notes. When the sales department needs to confirm product availability, warehouse staff routinely have to spend 5 to 10 minutes physically searching through the yard or cross-checking messy spreadsheets just to locate a specific construction item.

Managing construction materials across the distribution yard introduces additional organizational challenges. Xuan Thanh struggles with maintaining a consolidated view of actual inventory levels because warehouse items are not systematically organized or assigned to specific, traceable storage locations. Without a centralized system, critical inventory information is frequently scattered across different paper sheets or isolated files between the warehouse yard and the office. This makes daily logistics coordination extremely slow, error-prone, and highly dependent on the personal memory of individual workers.

Another common issue is inventory inaccuracy caused by manual ledger updates. After materials are received or shipped, records are not updated immediately, and human entry mistakes frequently occur. Furthermore, the company does not currently have a standardized process for tracking returned goods, natural inventory shrinkage, or real-time stock discrepancies. As a result, recorded entries fail to match actual physical stock levels, making it difficult for management to make accurate operational decisions. This data misalignment can lead to delayed deliveries, incorrect stock commitments to contractors, and unnecessary or mistimed purchasing decisions based on unreliable data.

As warehouse operations become more complex, Xuan Thanh faces severe bottlenecks in tracking inventory movements, monitoring stock history, and reviewing inbound/outbound transaction logs. Transaction records are completely frozen in paper logs, making it nearly impossible to quickly investigate discrepancies or find the root cause of stock loss. To compensate for this blindspot, a full physical inventory count must be performed at the end of each month. Each monthly audit typically consumes 4 to 6 working hours and completely paralyzes both warehouse personnel and accounting staff. Reconciling physical counts with recorded figures becomes a time-consuming and exhausting process due to incomplete transaction histories.

As Xuan Thanh Co., Ltd. continues to scale its business and transaction volumes, transitioning to a centralized warehouse management solution becomes a critical necessity. The business urgently needs an efficient tool to track product locations, monitor live inventory balances, record daily material variances, and access transaction history instantly. At the end of each month, the accounting and warehouse teams currently spend approximately one full working day manually collecting and consolidating data before physical stock summaries and movement reports can be produced. A dedicated, automated warehouse management system will eliminate this data lag, minimize operational errors, restore full inventory visibility, and protect the company from risks of financial loss.

# 2. Existing Solutions

## 2.1  Microsoft Excel

Microsoft Excel is one of the most commonly used tools for inventory tracking among small businesses. Companies often create their own spreadsheets to record stock levels, inbound and outbound transactions, and warehouse information manually.

| Attribute | Description |
| --- | --- |
| Website / Link | https://www.microsoft.com/excel |
| Target Users | Small businesses, warehouse operators, and inventory clerks |
| Core Features | Inventory tracking, spreadsheet-based data management, filtering, and reporting |
| Strengths | Easy to use, low cost, highly flexible, and familiar to most users |
| Weaknesses | Relies heavily on manual data entry, prone to human errors, difficult to manage large inventories, and lacks real-time synchronization |
| GAP for this project | Excel does not support centralized warehouse management, multi-warehouse operations, storage location management, inventory movement tracking, stock transfer workflows, or inventory traceability. |

## 2.2  Sapo

Sapo is a popular sales and inventory management platform in Vietnam that helps businesses manage products, orders, and stock levels across retail channels.

| Attribute | Description |
| --- | --- |
| Website / Link | https://www.sapo.vn |
| Target Users | Retail stores and small-to-medium-sized businesses |
| Core Features | Product management, inventory tracking, order management, and reporting |
| Strengths | User-friendly interface, integrated sales and inventory management, suitable for SMEs |
| Weaknesses | Warehouse management capabilities are limited compared to dedicated warehouse management systems |
| GAP for this project | Sapo primarily focuses on sales and basic inventory control. It does not provide detailed warehouse structure management, storage location tracking, warehouse transfer management, or complete inventory traceability at the storage-location level. |

## 2.3  KiotViet

KiotViet is a cloud-based business management solution widely used by retailers in Vietnam. It provides inventory, sales, and customer management functions for stores and retail chains.

| Attribute | Description |
| --- | --- |
| Website / Link | https://www.kiotviet.vn |
| Target Users | Retail businesses and store chains |
| Core Features | Inventory management, sales management, customer management, and reporting |
| Strengths | Easy deployment, cloud-based architecture, and support for multiple branches |
| Weaknesses | Designed mainly for retail operations rather than warehouse-centric operations |
| GAP for this project | Although KiotViet supports inventory management across multiple branches, it lacks detailed storage location management, warehouse transfer workflows, inventory auditing processes, and comprehensive inventory movement tracking. |

# 3. Proposed Solution

The proposed Warehouse Management System (WMS) is designed to help businesses manage warehouse operations in a centralized and organized manner. The system addresses the challenges of managing inventory across multiple warehouses by providing a single platform for tracking warehouse information, product data, inventory transactions, and stock movements. Instead of relying on spreadsheets or disconnected processes, businesses can maintain a consistent and accurate view of their inventory across all warehouse locations.

The primary beneficiaries of this solution are warehouse managers, warehouse staff, purchasing staff, and sales staff. Warehouse managers gain better visibility into inventory levels and warehouse operations, enabling faster and more informed decision-making. Warehouse staff can spend less time searching for products and performing manual inventory checks, while purchasing and sales teams can access more reliable inventory information when planning purchases or fulfilling customer orders. This helps reduce operational errors, improve coordination between departments, and increase overall efficiency.

This solution is particularly relevant as businesses continue to expand their product catalogs, warehouse networks, and transaction volumes. Managing inventory manually becomes increasingly difficult when products are distributed across multiple warehouses and storage locations. A centralized warehouse management approach provides better control over inventory movements, improves inventory accuracy, and supports business growth without significantly increasing administrative workload.

By providing a structured way to manage warehouses, products, suppliers, inbound and outbound operations, inventory audits, warehouse transfers, and reporting activities, the proposed system directly addresses the operational challenges identified in the previous section. The result is improved inventory visibility, more efficient warehouse operations, and a stronger foundation for future business expansion.

# 4. Project Scope & Limitations

## 4.1  Major Features

| ID | Feature Name | Description | Addresses Gap |
| --- | --- | --- | --- |
| FE-01 | Warehouse Management | Enables businesses to manage multiple warehouses, storage structures, capacity information, and product locations within a centralized system. | GAP-01, GAP-02 |
| FE-02 | Product Management | Provides a centralized product catalog with product classification, attributes, units of measure, barcode information, and traceability data. | GAP-02, GAP-04 |
| FE-03 | Supplier Management | Maintains supplier information, supplied product catalogs, and transaction history to improve procurement visibility. | GAP-05 |
| FE-04 | Inbound Management | Supports receiving goods from suppliers, assigning storage locations, and updating inventory records accurately. | GAP-03, GAP-04 |
| FE-05 | Outbound Management | Supports warehouse outbound operations, inventory validation, shipment processing, and transaction tracking. | GAP-03, GAP-04 |
| FE-06 | Stock Taking | Enables inventory counting, discrepancy recording, and inventory adjustment to improve inventory accuracy. | GAP-06 |
| FE-07 | Warehouse Transfer | Supports transferring products between warehouses or storage locations while maintaining inventory traceability. | GAP-01, GAP-07 |
| FE-08 | Reporting & Analytics | Provides inventory reports, stock movement reports, warehouse performance statistics, and supplier-related analytics. | GAP-08 |

| Gap ID | Description |
| --- | --- |
| GAP-01 | Difficulty managing inventory across multiple warehouses |
| GAP-02 | Difficulty locating products and tracking storage locations |
| GAP-03 | Inventory records not matching actual stock levels |
| GAP-04 | Inefficient tracking of inbound and outbound inventory transactions |
| GAP-05 | Limited visibility into supplier-related activities |
| GAP-06 | Time-consuming manual inventory counting and reconciliation |
| GAP-07 | Challenges in managing stock transfers between warehouses |
| GAP-08 | Lack of centralized reporting and operational visibility |

## 4.2  Limitations & Exclusions

| ID | Excluded Item | Reason |
| --- | --- | --- |
| LI-01 | Mobile Application (iOS/Android) | The first version focuses on a web-based system to validate core warehouse management workflows. |
| LI-02 | Barcode Scanner Hardware Integration | The system stores barcode information but does not integrate directly with physical barcode scanning devices in this version. |
| LI-03 | RFID Integration | RFID infrastructure requires additional hardware investment and is outside the scope of this project. |
| LI-04 | ERP Integration | Integration with ERP systems is deferred to future phases after validating core warehouse operations. |
| LI-05 | AI-Based Demand Forecasting | Demand forecasting requires historical business data and advanced analytics capabilities that are outside the scope of version 1. |
| LI-06 | Transportation and Delivery Management | The system focuses on warehouse operations and does not manage vehicle routing or delivery logistics. |
| LI-07 | Financial and Accounting Management | Financial transactions, invoicing, and accounting processes are handled by external systems. |
| LI-08 | Automated Warehouse Equipment Control | The system does not control conveyors, robotic systems, or other warehouse automation equipment. |

# 5. Expected Contributions & Next Steps

## 5.1  Business & Operational Impact

The proposed Warehouse Management System is expected to help small and medium-sized businesses operate their warehouses in a more professional and structured manner. By replacing manual processes and spreadsheet-based inventory tracking, businesses can reduce operational costs associated with inventory discrepancies, product searching, and repetitive administrative work.

The system provides greater visibility into warehouse operations, enabling businesses to manage multiple warehouses, monitor inventory levels, and track product movements more effectively. This reduces the risk of stock inaccuracies, improves inventory control, and supports faster decision-making.

By standardizing warehouse processes such as receiving, storing, transferring, counting, and shipping goods, the system helps businesses establish a more organized and professional warehouse operation model. As a result, small and medium-sized enterprises can improve operational efficiency, reduce management costs, minimize inventory discrepancies, and gain better control over inventory across multiple warehouse locations. The system also provides a solid foundation for future business growth while maintaining simplicity and ease of use.

## 5.2  User Experience Impact

Warehouse managers benefit from having a centralized view of warehouse operations, inventory levels, and stock movements across all warehouse locations. This improves visibility and reduces the effort required to monitor daily warehouse activities and make operational decisions.

Warehouse staff can locate products more quickly, record inventory transactions more accurately, and perform stock counting activities with less manual effort. Access to structured warehouse and storage location information helps reduce confusion and improves daily productivity.

Purchasing staff gain better visibility into supplier information and inventory status, allowing them to make purchasing decisions based on more reliable data. Sales staff can access up-to-date inventory information when processing customer requests, reducing delays caused by inventory uncertainty and improving customer service quality.

Overall, users benefit from a more organized workflow, reduced dependency on spreadsheets, and easier access to warehouse-related information through a single centralized system.

## 5.3  Planned Next Steps After Project Completion

Following the successful completion of the first version of the Warehouse Management System, several enhancements can be considered in future development phases. One potential improvement is the integration of barcode scanning devices to increase the speed and accuracy of inventory operations. Mobile support may also be introduced to allow warehouse staff to perform warehouse activities directly from handheld devices.

Additional reporting capabilities and advanced analytics can also be explored to provide deeper insights into inventory trends, warehouse utilization, and operational performance. These improvements would help businesses optimize warehouse operations and support data-driven decision-making.

As businesses continue to grow, the system can be expanded with features such as RFID integration, automated warehouse equipment support, and demand forecasting capabilities. These enhancements would further improve warehouse efficiency and support larger-scale warehouse operations in the future.

— End of Document —