Project Management Plan

Building Materials Warehouse Management System (BMWMS) – Report 2

| Version | 1.0 |
| --- | --- |
| Date | 01/06/2026 |

# Change Log

| Version | Date | Author | Summary |
| --- | --- | --- | --- |
| 1.0 | 01/06/2026 | Tran Duc Thang | Initial plan |

# Table of Contents

Change Log	1

Table of Contents	2

1. Project Overview	3

1.1 System Description	3

1.2 Technical Scope Summary	3

2. Development Team	3

2.1 Team Structure	3

2.2 RACI by Deliverable Type	3

2.3 Capacity Planning	4

3. Deliverable & Scope	4

3.1 Timeline Overview	5

3.2 Project Deliverables	5

3.3 Scope and Workload	6

a. Iteration 1 (Weeks 5–7)	6

b. Iteration 2 (Weeks 8–10)	7

c. Iteration 3 (Weeks 11–13)	7

4. Risks and Mitigations	8

5. Communication Plan	9

6. Configuration Management	9

6.1 Document Management	9

6.2 Source Code Management	10

6.3 Tools & Infrastructures	10

# 1. Project Overview

## 1.1 System Description

BMWMS (Building Materials Warehouse Management System) is a web-based warehouse management system designed for construction material trading companies. The system helps warehouse managers and warehouse staff manage inventory, inbound and outbound operations, stock taking, warehouse transfers, supplier information, and reporting activities in a centralized platform, replacing manual spreadsheet and paper-based processes.

## 1.2 Technical Scope Summary

| Metric | Value |
| --- | --- |
| Business Flows | 10 (BF01–BF10) |
| Actors / Roles | 5 |
| Use Cases | 89 (UC01–UC89) |
| Total FT-IDs | 27 Features |
| Screens / Pages | 60+ Screens |
| Background Jobs | 3 (Low Stock Alert, Inventory Recalculation, Scheduled Reports) |

# 2. Development Team

## 2.1 Team Structure

| Role | Code | Primary responsibilities |
| --- | --- | --- |
| Business Analyst / Project Manager | BA | Requirement elicitation, PRD, Use Case Specification, Feature Design Specification, project planning, sprint coordination, user manual, final documentation. |
| Developer 1 (Team Lead) | D1 | System architecture, database design, code review, deployment support, development of Module 1 (Warehouse Management) and Module 2 (Product Management). |
| Developer 2 | D2 | Development of Module 3 (Supplier Management), Module 4 (Inbound Management), and related integration tasks. |
| Developer 3 | D3 | Development of Module 5 (Outbound Management), Module 6 (Stock Taking), Module 7 (Warehouse Transfer), and Module 8 (Reporting & Analytics). |
| QA Engineer (Tester) | QA | Test planning, test case design, system testing, integration testing, defect tracking, UAT support, test reporting. |

## 2.2 RACI by Deliverable Type

R~Responsible (does the work)  ·  A~Accountable (approves quality)  ·  C~Consulted  ·  I~Informed

| Deliverable | TL | BA | D1 | D2 | QA |
| --- | --- | --- | --- | --- | --- |
| Deliverable | BA | D1 (TL) | D2 | D3 | QA |
| Vision & Scope | R/A | C | I | I | I |
| Project Management Plan | R/A | C | I | I | I |
| PRD | R/A | C | C | C | C |
| UCS | R/A | C | C | C | C |
| FDS | R/A | C | I | I | C |
| Database Design | C | R/A | C | C | I |
| Architecture Design | C | R/A | I | I | C |
| Test Plan | C | C | I | I | R/A |
| Feature Code – Module 1-2 | I | A/R | I | I | I |
| Feature Code – Module 3-4 | I | A | R | I | I |
| Feature Code – Module 5-8 | I | A | I | R | I |
| L1 Unit Tests | I | R | R | R | C |
| L2 Integration Tests | I | C | R | R | C |
| L3 System Tests | I | I | I | I | R/A |
| L4 UAT Support | C | I | I | I | R |
| Bug Fixing | I | R | R | R | C |
| Deployment Guide | C | R/A | I | I | I |
| User Manual | R/A | C | I | I | C |
| Final Report | R/A | C | I | I | C |

## 2.3 Capacity Planning

| Item | Value |
| --- | --- |
| Hours per person per week | 40 h |
| Team total per week | 200 h/week |
| Total duration | 14 weeks |
| Gross capacity | 2,800 h |
| Buffer (20%) | 560 h |
| Effective working capacity | 2,240 h |

# 3. Deliverable & Scope

## 3.1 Timeline Overview

| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase | Phase 1 | Phase 1 | Phase 1 | Phase 1 | Iter 1 | Iter 1 | Iter 1 | Iter 2 | Iter 2 | Iter 2 | Iter 3 | Iter 3 | Iter 3 | Closure |
| Deliverable | Planning | Analysis | Design | Design | Build | Build | Test | Build | Build | Test | Build | Build | UAT | Final |

| Role | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TL | Arch | Arch | DBD | Rev | CR | Rev | Int | Rev | Int | Rev | DG | E2E | E2E | DEP |
| BA | V&S | PRD | UCS1 | FDS1 | UCS2 | FDS2 | Rev | SS | Rev | SS | UM | UM | UAT | FR |
| D1 | Env | M01 | M02 | M02 | Code | Code | UT | M04 | M04 | IT | M06 | M07 | Fix | DEP |
| D2 | Env | M03 | M03 | M05 | Code | Code | UT | M05 | M05 | IT | M08 | M08 | Fix | DEP |
| QA | Setup | TC | TC | TP | TD | Rev | L3 | TD | Rev | L3 | Reg | E2E | UAT | AT |

## 3.2 Project Deliverables

| Deliverable | Completion phase / Deadline | Owner |
| --- | --- | --- |
| Vision & Scope | Phase 1 – Week 1 | BA |
| Project Management Plan v1.0 | Phase 1 – Week 1 | BA |
| PRD v1.0 | Phase 1 – Week 2 | BA |
| Architecture Design | Phase 1 – Week 3 | TL |
| Database Design | Phase 1 – Week 3 | TL |
| UCS v1.0 (M01–M04) | Phase 1 – Week 3 | BA |
| FDS v1.0 (M01–M04) | Phase 1 – Week 4 | BA |
| Test Plan v1.0 | Phase 1 – Week 4 | QA |
| UCS v1.0 (M05–M08) | Iteration 1 – Week 5 | BA |
| FDS v1.0 (M05–M08) | Iteration 1 – Week 6 | BA |
| Software Package – Iteration 1 (M01–M03) | Iteration 1 – Week 7 | TL + Dev |
| Unit & Integration Test Report – Iteration 1 | Iteration 1 – Week 7 | QA |
| Software Package – Iteration 2 (M04–M05) | Iteration 2 – Week 10 | TL + Dev |
| Unit & Integration Test Report – Iteration 2 | Iteration 2 – Week 10 | QA |
| Software Package – Iteration 3 (M06–M08) | Iteration 3 – Week 12 | TL + Dev |
| System Test & E2E Report | Iteration 3 – Week 13 | QA |
| UAT Sign-off Report | Iteration 3 – Week 13 | QA + BA |
| Deployment Guide | Phase 3 – Week 14 | TL |
| User Manual | Phase 3 – Week 14 | BA |
| Final Report | Phase 3 – Week 14 | BA |
| Project Handover Package | Phase 3 – Week 14 | TL + BA |

## 3.3 Scope and Workload

### a. Iteration 1 (Weeks 5–7)

Business Outcome: Foundation master data management for warehouse operations.

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-01 | Manage Warehouse | Must | Warehouse Management | UC01-UC05 | SC-01 |
| FT-02 | Manage Storage Location | Must | Warehouse Management | UC06-UC09 | SC-01 |
| FT-03 | Locate Product | Should | Warehouse Management | UC10 | SC-07 |
| FT-04 | Manage Product | Must | Product Management | UC11-UC15 | SC-02 |
| FT-05 | Manage Product Group | Must | Product Management | UC16-UC18 | SC-02 |
| FT-06 | Manage Product Attributes | Must | Product Management | UC19-UC20 | SC-02 |
| FT-07 | Product Transaction History | Should | Product Management | UC21 | SC-07 |
| FT-08 | Manage Supplier | Must | Supplier Management | UC22-UC26 | SC-03 |
| FT-09 | Supplier Product Management | Must | Supplier Management | UC27 | SC-03 |
| FT-10 | Supplier Transaction History | Should | Supplier Management | UC28 | SC-03 |

End-of-Iteration-1 Outcome

Users can manage warehouse structures, products, product attributes, and suppliers. The system provides complete master data required for warehouse operations.

### b. Iteration 2 (Weeks 8–10)

Business Outcome: Inventory receiving and issuing processes are operational.

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-11 | Manage Inbound Voucher | Must | Inbound Management | UC29-UC33 | SC-04 |
| FT-12 | Perform Receiving | Must | Inbound Management | UC34-UC35 | SC-04 |
| FT-13 | Inbound History | Should | Inbound Management | UC36 | SC-04 |
| FT-14 | Manage Outbound Voucher | Must | Outbound Management | UC37-UC41 | SC-05 |
| FT-15 | Stock Availability Check | Must | Outbound Management | UC42 | SC-05 |
| FT-16 | Perform Outbound | Must | Outbound Management | UC43 | SC-05 |
| FT-17 | Outbound History | Should | Outbound Management | UC44 | SC-05 |

End-of-Iteration-2 Outcome

Warehouse staff can receive goods, issue goods, and maintain accurate inventory records. Stock availability is validated before outbound transactions.

### c. Iteration 3 (Weeks 11–13)

Business Outcome: Inventory control, transfer, and reporting functions are completed.

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-18 | Stocktake Planning | Must | Audit | UC45-UC47 | SC-08 |
| FT-19 | Execute Stocktake | Must | Audit | UC48-UC49 | SC-08 |
| FT-20 | Inventory Adjustment | Must | Audit | UC50 | SC-09 |
| FT-21 | Stocktake History | Should | Audit | UC51 | SC-08 |
| FT-22 | Transfer Request Management | Must | Transfer | UC52-UC55 | SC-06 |
| FT-23 | Execute Transfer | Must | Transfer | UC56-UC57 | SC-06 |
| FT-24 | Inventory Reports | Must | Reporting | UC58-UC62 | SC-10 |
| FT-25 | Product Analytics | Should | Reporting | UC63-UC67 | SC-10 |
| FT-26 | Warehouse Analytics | Should | Reporting | UC68-UC72 | SC-10 |

End-of-Iteration-3 Outcome

Users can perform stocktaking, inventory adjustments, warehouse transfers, and generate management reports for warehouse operations.

# 4. Risks and Mitigations

| # | Risk | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | Requirements change during development | Medium | High | Freeze PRD and UCS after Week 4. Any change request must be reviewed by BA and approved by TL before implementation. |
| R02 | Delay in completing UI design and FDS documents | Medium | Medium | Prioritize core screens first. Complete UI and FDS one iteration ahead of development. |
| R03 | Integration issues between frontend and backend modules | Medium | High | Define API contracts before coding. Conduct integration testing at the end of each iteration. |
| R04 | Inventory transaction logic contains defects affecting stock accuracy | Medium | High | Implement unit tests for stock calculations and validate transaction flows with test scenarios before release. |
| R05 | Team members unavailable due to academic workload or exams | Medium | Medium | Maintain task buffer and cross-train team members to reduce dependency on a single developer. |
| R06 | Testing activities delayed due to late feature completion | Medium | High | Reserve buffer in Weeks 12–13 for regression testing and bug fixing before UAT. |
| R07 | UAT feedback requires significant rework | Low | High | Conduct internal review and demo after each iteration to identify issues before formal UAT. |
| R08 | Deployment environment differs from development environment | Low | Medium | Prepare deployment guide early and perform deployment rehearsal before final release. |
| R09 | Database design changes after development starts | Low | High | Finalize ERD and database schema during Phase 1 and review with the whole team before implementation. |
| R10 | Project schedule overrun near submission deadline | Medium | High | Track progress weekly, prioritize Must-have features, and postpone non-critical enhancements if required. |

# 5. Communication Plan

| Meeting | Frequency | Duration | Participants |
| --- | --- | --- | --- |
| Meeting | Frequency | Duration | Participants |
| Daily Stand-up | Every working day | 15 min | TL, BA, D1, D2, QA |
| Iteration Planning | Start of each iteration (Weeks 5, 8, 11) | 2 h | All |
| Weekly Progress Meeting | Every Friday | 30 min | All |
| Iteration Review (Demo) | End of each iteration (Weeks 7, 10, 13) | 1 h | All + Supervisor |
| Iteration Retrospective | After each review | 45 min | Team only |
| Requirements Review | Week 2 | 2 h | BA, TL, Dev Team |
| Design Review | Week 4 | 2 h | TL, BA, Dev Team |
| Test Plan Review | Week 4 | 1 h | QA, TL, BA |
| UAT Review | Week 13 | 1 h | BA, QA, Supervisor |
| Final Project Review | Week 14 | 1 h | All |

# 6. Configuration Management

## 6.1 Document Management

Project documents are stored and managed using Google Drive with role-based access control. All project members have access to shared project documents, while modification permissions are restricted based on responsibilities.

Document Versioning Rules

- Major versions: v1.0, v2.0, v3.0

- Minor revisions: v1.1, v1.2, v1.3

- All changes must be tracked using document version history.

- Only the document owner may approve major version updates.

- Final approved documents are marked as Baseline and stored in the Final Deliverables folder.

## 6.2 Source Code Management

Source code is managed using GitHub and follows a Git-based branching strategy.

Branch Structure

main

develop

feature/module-01

feature/module-02

feature/module-03

…

Source Control Rules

- main contains production-ready code only.

- develop contains integrated code for testing.

- Each feature is developed in a separate feature branch.

- Pull Requests are required before merging into develop.

- Code review must be approved by the Tech Lead.

- Commit messages follow the format:

[Module] Short description

Example:

[M01] Add warehouse creation API

[M04] Implement inbound voucher validation

Release Management

- Iteration 1 Release: Week 7

- Iteration 2 Release: Week 10

- Iteration 3 Release: Week 13

- Final Release: Week 14

## 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Razor Pages (.NET 8), ASP.NET Core Web API (.NET 8) |
| Database | Microsoft SQL Server 2022 |
| IDEs / Editors | Visual Studio 2022, Visual Studio Code |
| Diagramming | Draw.io, StarUML |
| Documentation | Microsoft Office 365, Google Docs, Google Sheets |
| Version Control | GitHub, Google Drive |
| Project Management | Jira, GitHub Projects |
| API Testing | Postman |
| UI/UX Design | Figma |
| Deployment Server | Windows Server / IIS |
| Source Repository | GitHub |
| Communication | Microsoft Teams, Discord |
| Testing Tools | xUnit, Swagger UI, Postman |
| Database Tools | SQL Server Management Studio (SSMS) |
| CI/CD (Optional) | GitHub Actions |